## project
Project Planner
[7 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | Names | START | DURATION | START | DURATION | COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Function Library | Natalia | 1 | 1 | 0 | 0 | 0%
Game Manager | Natalia | 1 | 4 | 0 | 0 | 0%
Character Setup | Pete | 1 | 2 | 0 | 0 | 0%
Basic Enemies | Jack | 1 | 3 | 0 | 0 | 0%
Store/Vendor | Peter | 1 | 2 | 0 | 0 | 0%
Spells | Pete | 3 | 1 | 0 | 0 | 0%
Abilities | Pete | 3 | 1 | 0 | 0 | 0%
Bad guy NPCs | Natalia | 3 | 1 | 0 | 0 | 0%
HUD | Natalia | 2 | 1 | 0 | 0 | 0%
Main Menu UI | Peter | 2 | 2 | 0 | 0 | 0%
Lose UI | Peter | 3 | 1 | 0 | 0 | 0%
Win UI | Peter | 3 | 1 | 0 | 0 | 0%
Level Design | TBA | 3 | 1 | 0 | 0 | 0%
Environment | TBA | 3 | 1 | 0 | 0 | 0%
Sound | Jack | 3 | 1 | 0 | 0 | 0%
Bug Fixes | Everyone | 4 | 1 | 0 | 0 | 0%
Bonus Content | bar: PERIODS 1 to PERIODS 20
Animations | Pete | 4 | 1 | 0 | 0 | 0%
Bigger Enemies | Jack | 4 | 1 | 0 | 0 | 0%
Friendly NPCs | Natalia | 4 | 1 | 0 | 0 | 0%
Activity 26 |  | 0 | 0 | 0 | 0 | 0%